

**15 July 2015**

**[14-15]**

**Administrative Assessment Report –Proposal M1013**

Schedule 20 – MRLs – Consequentials & Corrective Amendments

|  |  |
| --- | --- |
| **Brief Description of Proposal:**To update Schedule 20 (commencing 1 March 2016) to reflect amendments made to Schedule 1 of current Standard 1.4.2 in 2015 and to correct technical and formatting errors. | **Potentially affected Standard:**Schedule 20 (revised Code) |
| **Procedure:** Minor**Reasons why:**The proposal will make consequential changes and will not create or vary rights or obligations.  | **Estimated total hours:** Maximum 100 hours**Reasons why:**Amendments will reflect current requirements. | **Provisional estimated start work:** Early July 2015 |

|  |
| --- |
| **Other Comments or Relevant Matters:**To facilitate the project, the Standard will replace the complete Schedule with a new Schedule which will mirror Schedule 1 of current Standard 1.4.2 which will cease to have effect on 1 March 2016. |

***Decision***

|  |
| --- |
| **Proposal prepared**Date: **6 July 2015** |

***Consultation & assessment timeframe***

|  |
| --- |
| **Proposed length of public consultation period:** 4 weeks |
| **Proposed timeframe for assessment: 3 August 2015**Commence assessment (clock start) Early Sept 2015Completion of assessment & preparation of food reg measure Late Sept 2015Public comment Late Sept–late Oct 2015Board to complete approval Early Dec 2015Notification to Forum Mid-Dec 2015Anticipated gazettal if no review requested Late Feb 2016 |