

**3 August 2017**

**[20–17]**

**Administrative assessment report – Proposal M1015**

Maximum Residue Limits (2017)

|  |  |  |
| --- | --- | --- |
| **Brief Description of Proposal:**  To consider varying certain maximum residue limits (MRLs) for residues of specified agricultural and veterinary chemicals that may occur in food commodities. | | **Potentially affected standard:**  Schedule 20 of the Code |
| **Procedure:**  General | **Estimated total hours:**  Maximum 1000 hours  **Reasons why:**  Involves assessment of the public health and safety risk of residues of the requested chemicals in the specified food commodities to Australian consumers. | **Provisional estimated start work:**  Late July 2017 |

|  |
| --- |
| **Other Comments or Relevant Matters:**  The Proposal will consider varying certain MRLs in the *Australia New Zealand Food Standards Code* (the Code) to align with those established by Codex or trading partner standards for the requested agricultural and veterinary (agvet) chemicals for food import purposes.  This is a routine process that allows the sale of imported foodcommodities with legitimate residues of agvet chemicals used in their production. The use is consistent with international regulations for the safe and effective use of the agvet chemicals based on good agricultural practice.  This Proposal also includes consideration of MRL variations requested by the Australian Pesticides and Veterinary Medicines Authority (APVMA). The APVMA requests may be deletions, reductions or increases of a number of MRLs, as well as inclusions of new food commodities in Schedule 20, following the completion of chemical reviews. |

***Decision***

|  |
| --- |
| **Proposal prepared**  Date: 25 July 2017 |

***Consultation & assessment timeframe***

|  |
| --- |
| **Proposed length of public consultation period:**  4 weeks |
| **Proposed timeframe for assessment:**  Commence assessment (clock starts) Late July 2017  Completion of assessment & preparation of  draft food regulatory measure Late November 2017  Public comment period (4 weeks) Early February 2018  Board to complete approval Mid-June 2018  Notification to Forum Late June 2018  Anticipated gazettal if no review requested Late August 2018 |