

**27 February 2015**

**[03–15]**

**Administrative Assessment Report – Proposal P1037**

Amendments associated with Nutrition Content & Health Claims

|  |  |
| --- | --- |
| **Brief Description of Proposal:**To address inconsistencies and lack of clarity associated with Standard 1.2.7 and related standards to ensure that Standard 1.2.7 operates as intended and also to provide exemptions for certain Health Star Rating label elements from Standard 1.2.7 requirements.  | **Potentially affected Standards:**1.2.7, 1.2.8, 1.3.2 |
| **Procedure:** General  | **Estimated total hours:** Up to 350 **Reasons why:**No need for an assessment of the risk to public health and safety, limited economic impact, and likely to involve an assessment of risk management measures of less than average complexity.  | **Estimated start work:** Late February 2015 |

***Decision***

|  |
| --- |
| **Proposal prepared**Date: 23 February 2015 |

***Consultation & assessment timeframe***

|  |
| --- |
| **Proposed length of public consultation period:** 6 weeks  |
| **Proposed timeframe for assessment:**Commence assessment (clock start) Early March 2015Completion of assessment & preparation of draft food reg measure Early April 2015Public comment Early April – mid-May 2015Board to complete approval Mid Sept 2015Notification to Forum Early Oct 2015Anticipated gazettal if no review requested Mid-Dec 2015 |