

**20 August 2015**

**[19–15]**

**Administrative Assessment Report –Proposal P1040**

Code Revision – Consequential & Corrective Amendments II

|  |  |  |
| --- | --- | --- |
| **Brief Description of Proposal:**  To update the revised *Australia New Zealand Food Standards Code* to correct typographical and transcription errors. | | **Potentially affected Standards:**  Standards 1.1.1, 1.1.2, 1.2.7, 1.2.8, 1.4.1, 1.4.2, 1.5.2, 2.4.2, 2.7.1, 2.7.4, 2.9.4, 2.9.6, S1—2, S2—2, S4—2, S4—5, S12—4, S15, S18—3, S26 and S29—21 of the revised Code. |
| **Procedure:**  Minor  **Reasons why:**  The proposal will correct typographical and transcription errors in the revised Code. The Proposal will not create or vary rights or obligations. Nor will it alter the Code’s legal effect. | **Estimated total hours:**  Maximum 100 hours  **Reasons why:**  Amendments will reflect current requirements. | **Provisional estimated start work:**  Late August 2015 |

|  |
| --- |
| **Other Comments or Relevant Matters:** |

***Decision***

|  |
| --- |
| **Proposal prepared**  Date: 14 August 2015 |

***Consultation & assessment timeframe***

|  |
| --- |
| **Proposed length of public consultation period:**  4 weeks |
| **Proposed timeframe for assessment: 31 August 2015**  Commence assessment (clock start) Early Sept 2015  Completion of assessment & preparation of food reg measure Late Sept 2015  Public comment Late Sept–late Oct 2015  Board to complete approval Early Dec 2015  Notification to Forum Mid-Dec 2015  Anticipated gazettal if no review requested Late Feb 2016 |